## Tracker
SEO audit tracker: [example.com]
Fill in the yellow cells, one row per problem: a problem in a template is one row, with the number of pages the one fix covers. Severity, Effort and Status have drop-down lists. Row 5 is an example of the format; replace it. A filled-in example is on the sheet "Example (demo shop)".
# | Problem | Check | Pages | Where (template) | Severity | Effort | Fix | Owner | Due | Status | Notes
1 | Product pages have no canonical tag | INDEX-003 | 30 | /shop/*/* | Warning | Low | Add a self-referencing canonical to the product template | Developer |  | In progress | One template, all products

## Summary
Summary
Counted from the sheet "Tracker" with formulas; it updates as you fill it in.
Problems by severity
Critical
Warning
Notice
Problems by status
To do
In progress
Done
Accepted as intended
Open work
Problems still open (To do or In progress)
Pages those open problems cover

## Example (demo shop)
Example: the Trakis demo shop
From the Trakis audit of demo.trakis.io on 14 October 2026: 42 pages read, each problem once. The full report is at trakis.io/example. The demo shop sells nothing; its mistakes were put in on purpose.
# | Problem | Check | Pages | Where (template) | Severity | Effort | Fix | Owner | Due | Status | Notes
1 | Response other than 200 | CRAWL-002 | 1 | /returns | Critical | Low | These addresses answer with an error. If the page should exist, restore it; if it moved, redirect it with a 301; if it is gone for good, answer 410 and remove the links to it. |  |  | To do
2 | robots.txt keeps AI search out | AI-005 | 1 | (site) | Warning | Medium | robots.txt keeps OAI-SearchBot out. Answer bots and training bots have different names, so one can be let in and the other kept out. |  |  | To do
3 | Internal links to dead pages | LINK-004 | 1 | (site) | Warning | Medium | Fix the link once, in the menu or footer template: point it at the page it meant, or remove it. |  |  | To do
4 | Thin content | CONTENT-001 | 40 | (whole site) | Warning | Low | Look at which pages are short and whether they are meant to rank. |  |  | To do
5 | Images without alternative text | CONTENT-002 | 30 | /shop/boots/*, /shop/sandals/*, /shop/sneakers/* | Warning | Low | Write an alt text for each image that carries meaning: what it shows, in a few words ("brown leather Chelsea boot, side view"). |  |  | To do
6 | Duplicate meta descriptions | CONTENT-006 | 30 | /shop/boots/*, /shop/sandals/*, /shop/sneakers/* | Warning | Low | Give each of these pages a description of its own: one or two sentences on what this page holds that the others do not, written for someone choosing between results. |  |  | To do
7 | Canonical missing | INDEX-003 | 30 | /shop/boots/*, /shop/sandals/*, /shop/sneakers/* | Warning | Low | Every page should name its own address as canonical — the full address, with https and the site's one host. |  |  | To do
8 | Product without price or availability | STRUCT-004 | 30 | /shop/boots/*, /shop/sandals/*, /shop/sneakers/* | Warning | Low | Add an "offers" object to the Product with "price", "priceCurrency" and "availability", filled from the shop’s own data. |  |  | To do
9 | Pages that repeat each other’s text | CONTENT-008 | 1 | /shop/sneakers/* | Warning | Low | Keep one page for the text and point the others at it with a canonical, or redirect them with a 301. |  |  | To do
10 | Redirect chain | CRAWL-003 | 1 | /shop/boots | Warning | Low | Point the first redirect straight to the final address. |  |  | To do
11 | Orphan pages | LINK-005 | 1 | /landing/winter | Warning | Low | Link each orphan from the page it belongs under — its category, or a related article. |  |  | To do
12 | Title too long | ONPAGE-002 | 3 | /shop/boots, /shop/sandals, /shop/sneakers | Warning | Low | Write a <title> of 30–70 characters for each page: what the page is, then the site's name. The first 60 are the ones shown almost everywhere. |  |  | To do
13 | H1 missing | ONPAGE-006 | 3 | /shop/boots, /shop/sandals, /shop/sneakers | Warning | Low | Give each of these pages exactly one <h1> that says what the page is about — for a category, its name ("Evening dresses"), not the site's name. |  |  | To do
14 | The page has no structured data | STRUCT-001 | 11 | /, /about, /blog/new-season, /contact, /guides/care, /guides/size-guide, /landing/winter, /search, /shop/boots, /shop/sandals, /shop/sneakers | Warning | Low | Give these pages a JSON-LD block that says what they are: WebPage at the least, Product for a product, BreadcrumbList for where it sits. |  |  | To do
15 | Home page without Organization | STRUCT-006 | 1 | / | Warning | Low | Add this block to the home page, inside <head>. Fill in the logo and the social profiles; the rest is this site already. |  |  | To do
16 | Sitemap lists pages that should not be there | CRAWL-010 | 1 | (site) | Warning | Medium | Generate the sitemap from the pages as they are now: only addresses that answer 200, with no redirect. |  |  | To do
17 | Deep page without a breadcrumb | STRUCT-007 | 30 | /shop/boots/*, /shop/sandals/*, /shop/sneakers/* | Notice | Low | Add a BreadcrumbList to the JSON-LD of the template, built from the same path the visible breadcrumb shows: the home page, each section, then the page itself. |  |  | To do
18 | Pages reached by one internal link only | LINK-007 | 24 | /shop/sandals/*, /shop/sneakers/*, /shop/boots/* | Notice | Low | Link to the page from two or three related pages, in the text, with words that say what it is. |  |  | To do
19 | No author or organisation signal | AI-004 | 1 | /landing/winter | Notice | Low | Say who stands behind the content: an author with a name on articles, the company on everything else. |  |  | To do
20 | The title is nowhere in the H1 | CONTENT-003 | 1 | /guides/care | Notice | Low | Make the title and the H1 say the same thing in different lengths: the H1 for the reader on the page, the title for the results. |  |  | To do
21 | Very low text-to-HTML ratio | CONTENT-004 | 3 | /shop/boots, /shop/sandals, /shop/sneakers | Notice | Low | The pages carry far more code than text. Move scripts and styles into files the browser caches, and remove templates the page does not use. |  |  | To do
22 | HSTS header missing | CRAWL-012 | 1 | / | Notice | Low | Send Strict-Transport-Security: max-age=31536000 from the server or the CDN (on Cloudflare: SSL/TLS, Edge Certificates, HSTS). |  |  | To do
23 | meta robots noindex | INDEX-001 | 1 | /search | Notice | Low | Check whether the page is meant to be in search. |  |  | To do
24 | Meta description outside the useful range | ONPAGE-005 | 1 | /search | Notice | Low | Write a meta description of 70–155 characters for each page: what the reader finds there and why to click. |  |  | To do